## Dashboard
Cabbo Customer Frontend QA Checklist(Local Env)
Generated for local QA run
Total checklist items | 56
Passed | 56
Failed | 0
Blocked | 0
Not started | 0
Open P0/P1 defects | 0
Local environment | Frontend local + backend local + Razorpay test mode
Trip types | Local hourly rental; airport pickup; airport drop-off; outstation

## Test Accounts
Persona | Phone Verified | Email Verified | Use For | Login Identifier | Password / OTP Notes | Notes
Customer A (Ayan) | Yes | Yes | Login, profile verified-email checks, normal booking/payment flows | 9831305667 | Successful login/onboarding with OTP | ayanchax9088@gmail.com
Customer B (Oyendrila) | Yes | No | Email-unverified profile and verification recovery checks | 8017084241 | Successful login/onboarding with OTP | NA

## Checklist
Section | Area | Trip Type | Customer Persona | Task | Expected Result | Status | Tester | Date | Evidence Link | Issue Link | Notes
Setup | Customer accounts | All | Phone verified / email verified | Sign in with verified-email customer | Login works and profile shows email verified | Success | Swaroop | 2026-07-05
Setup | Customer accounts | All | Phone verified / email unverified | Sign in with unverified-email customer | Login works and profile shows email unverified state | Success | Swaroop | 2026-07-05
1 | Search card | All trip types | Either | Search pickup and drop locations | Pickup/drop values remain stable after selection | Success | Swaroop | 2026-07-05
1 | Search card | All trip types | Either | Select recent location suggestions | Recent suggestions are ordered by latest selection | Success | Swaroop | 2026-07-05
1 | Search card | All trip types | Either | Use current location from pickup field | Current location is user-triggered and not forced on mount | Success | Swaroop | 2026-07-05
1 | Search card | All trip types | Either | Clear pickup/drop and reselect | Old suggestions/loading states do not clash | Success | Swaroop | 2026-07-05
1 | Classification | Local hourly | Either | Search local-city style route | User lands on local hourly flow | Success | Swaroop | 2026-07-05
1 | Classification | Airport pickup | Either | Search airport pickup route | User lands on airport pickup flow | Success | Swaroop | 2026-07-05
1 | Classification | Airport drop-off | Either | Search airport drop route | User lands on airport drop-off flow | Success | Swaroop | 2026-07-05
1 | Classification | Outstation | Either | Search outstation route | User lands on outstation flow | Success | Swaroop | 2026-07-05
1 | Preferences | All trip types | Either | Set preferences, go to results, navigate back | Date/time, passengers, luggage, airport fields, hops, and return date restore correctly | Success | Swaroop | 2026-07-05
2 | No rides | All trip types | Either | Search with high passenger/luggage preferences | Friendly no-rides state appears with no raw backend error | Success | Swaroop | 2026-07-05
2 | API failure | All trip types | Either | Trigger location/search/package API error | Readable error state with useful recovery; no stale data confusion | Success | Swaroop | 2026-07-05
3 | Ride selection | All trip types | Either | Review ride option list | Options sort/rank correctly; fare and policy link are clear | Success | Swaroop | 2026-07-05
3 | Ride metadata | All trip types | Either | Check best-choice, roof-carrier, add-on, and disclaimer display | Tags appear only where backend marks them and text is readable | Success | Swaroop | 2026-07-05
3 | Outstation details | Outstation | Either | Review trip days, included kms, round-trip copy, and route timeline | Outstation-specific details are accurate and not misleading | Success | Swaroop | 2026-07-05
4 | Payment success | All trip types | Either | Complete Razorpay test payment | Backend verifies payment and confirmed booking ID appears | Success | Swaroop | 2026-07-05
4 | Payment failure | All trip types | Either | Cancel/fail Razorpay payment | User can retry; cleanup is attempted; no confirmed booking is created | Success | Swaroop | 2026-07-05
4 | Payment retry | All trip types | Either | Fail, retry, then complete payment | Booking confirms once with no duplicate confirmed bookings | Success | Swaroop | 2026-07-05
4 | Payment refresh | All trip types | Either | Refresh before payment and after success | Pre-payment is recoverable; confirmed state survives refresh | Success | Swaroop | 2026-07-05
4 | Abandoned payment | All trip types | Either | Open checkout and abandon payment | No confirmed booking; customer can safely start again | Success | Swaroop | 2026-07-05
5 | Booking deep links | All trip types | Either | Load /booking/:bookingId directly | Booking detail loads after refresh | Success | Swaroop | 2026-07-05
5 | Booking errors | All trip types | Either | Open invalid and unauthorized booking IDs | Friendly error; unauthorized details are not exposed | Success | Swaroop | 2026-07-05
6 | My Trips tabs | All | Either | Test Upcoming, Ongoing, and Past tabs | Tab persists in URL and loading/empty states are correct | Success | Swaroop | 2026-07-05
6 | My Trips pagination | All | Either | Use next/previous pages | Pagination works and scrolls to top after page changes | Success | Swaroop | 2026-07-05
6 | Trip cards | All | Either | Review trip card fields and navigation | Cards show correct summary and route to canonical detail page | Success | Swaroop | 2026-07-05
7 | Status matrix | Confirmed/upcoming | Either | Open confirmed/upcoming booking | Allowed operational edit surfaces appear | Success | Swaroop | 2026-07-05
7 | Status matrix | Ongoing | Either | Open ongoing booking | Active support/fare context remains clear | Success | Swaroop | 2026-08-16
7 | Status matrix | Completed/closed | Either | Open completed/closed booking | Paid-to-driver/review behavior is correct | Success | Swaroop | 2026-08-16
7 | Status matrix | Cancelled | Either | Open cancelled booking | Refund summary is primary financial status | Success | Swaroop | 2026-07-05
7 | Status matrix | Dispute | Either | Open dispute booking | Blocked state replaces self-service actions | Success | Swaroop | 2026-08-16
7 | Status matrix | Stale past-active | Either | Open stale past-active booking | Balance pending marker appears | Success | Swaroop | 2026-08-16
8 | Driver assignment | All | Either | Open booking with assigned driver | Only customer-safe driver/cab fields appear and call action works | Success | Swaroop | 2026-08-16
8 | Driver assignment | All | Either | Open booking without assigned driver | Unassigned message is understandable and layout holds | Success | Swaroop | 2026-07-05
9 | Support | Each booking detail type | Either | Open support, call, WhatsApp, and policy link | Support is lazy-fetched; WhatsApp has booking context only | Success | Swaroop | 2026-07-05
9 | Special request | Eligible booking | Either | Add valid special request and reopen detail | Request saves once and becomes read-only | Success | Swaroop | 2026-07-05
9 | Special request validation | Eligible booking | Either | Try empty and overlong requests | The Save button will not enable if empty. Cannot enter more than 300 characters | Success | Swaroop | 2026-07-05
10 | Cancellation | Eligible upcoming | Either | Cancel with predefined and Other reasons | Warning appears; backend receives customer-safe payload; actions disappear | Success | Swaroop | 2026-07-05
10 | Refund | Cancelled booking | Either | Open cancelled booking with refund detail | Refund amount, type, status, and policy link are clear | Success | Swaroop | 2026-07-05
11 | Profile | Verified-email customer | Email verified | Update profile name and upload valid PNG | Profile updates without full-page confusion; PNG uploads | Success | Swaroop | 2026-07-05
11 | Profile validation | Either | Either | Try non-PNG and over-2-MB PNG | Friendly validation; invalid images are rejected | Success | Swaroop | 2026-07-05
11 | Email verification | Unverified-email customer | Email unverified | Resend or open verification flows where available | Verification status and recovery states are clear | Success | Swaroop | 2026-07-05
11 | Logout | Either | Either | Log out | Auth and customer-specific cache clear; navigation returns to login | Success | Swaroop | 2026-07-05
11 | Legal pages | All | Either | Open legal/support links from profile, login, fare, support, refund | Pages scroll top, title once, dates visible, links clickable, refresh works | Success | Swaroop | 2026-07-05
12 | Responsive | Mobile small | Either | Run visual pass | No horizontal scroll; important actions reachable | Success | Swaroop | 2026-07-05
12 | Responsive | Mobile large | Either | Run visual pass | Text/buttons/cards do not overflow | Success | Swaroop | 2026-07-05
12 | Responsive | Tablet | Either | Run visual pass | Trip cards and fare/payment sections remain readable | Success | Swaroop | 2026-07-05
12 | Responsive | Laptop | Either | Run visual pass | Layout is balanced and actions remain reachable | Success | Swaroop | 2026-07-05
12 | Responsive | Desktop/wide | Either | Run visual pass | No awkward stretching or overlap | Success | Swaroop | 2026-07-05
13 | Keyboard/accessibility | Core flows | Either | Keyboard-only pass across login, search, preferences, payment, booking, profile, legal | Tab order, focus, names, labels, and errors are usable | Success | Swaroop | 2026-07-05
14 | Loading/degraded | Core flows | Either | Test slow API/failure/empty states | Scoped loaders, friendly empty states, useful retries, no raw internals | Success | Swaroop | 2026-07-05
15 | Cross-browser smoke | Chrome latest | Either | Smoke login, search, ride options, profile, legal, booking detail | Smoke flow passes | Success | Swaroop | 2026-07-05
15 | Cross-browser smoke | Edge latest | Either | Smoke login, search, ride options, profile, legal, booking detail | Smoke flow passes | Success | Swaroop | 2026-07-05
15 | Cross-browser smoke | Safari iOS/Opera/Firefox if available | Either | Smoke login, search, ride options, profile, legal, booking detail | Smoke flow passes | Success | Swaroop | 2026-07-05
15 | Cross-browser smoke | Android Chrome if available | Either | Smoke login, search, ride options, profile, legal, booking detail | Smoke flow passes | Success | Swaroop | 2026-07-05
Completion | Release gate | All | Either | Confirm all trip types pass matrix | No P0; P1 fixed or accepted; evidence exists for critical flows | Success | Swaroop | 2026-08-16
StatusList
Not Started
In Progress
Success
Failed
Blocked

## Defects Log
ID | Date | Checklist Row / Area | Segment | Severity | Status | Owner | Notes
BUG-001 | 2026-07-05 | Setup | All trip types ¦ Frontend | P1 | Closed | Swaroop | P1- on adding a email from profile, email is added but also the Resend verification link appears - which ideally should not appear, because once a email is added, a verification email is sent to that email and if the user does not verify within more than 2 hours - then only it shows. However, on page refresh the Resend verification link does nota appear anymore. This is a UI rendering issue just after adding the email.
BUG-002 | 2026-07-05 | Search card | All trip types ¦ Frontend | P0 | Closed | Swaroop | P0: Recent suggestions are orderedby the latest one only when we do a real search and pick up the location, but if we pick up from a cached suggestion - then it does not shift that suggestion to the latest/on top of the order. The ordering works correctly only for API fetched suggestions.
BUG-003 | 2026-07-05 | Booking errors | All trip types ¦ Frontend | P0 | Closed | Swaroop | P0: Currently it shows a generic Error Boundary Component - Like We've hit a speed bump as we throw error on api data not found - but for this case - we need to show a specific trip not found feedback state. API Error { "detail": "Trip booking not found", "error": "Trip booking not found (status_code=404)", "error_code": "TRIP_NOT_FOUND" }
BUG-004 | 2026-07-05 | Trip cards | All trip types ¦ Frontend | P0 | Closed | Swaroop | P0: The card information in trip feed is correct - but the sorting in the card is not right. It is currently sorted from descending order of trip date whereas it should be in ascending order - recent upcoming first.
BUG-005 | 2026-07-05 | Special requests | Eligible booking ¦ Frontend | P0 | Closed | Swaroop | P0: The Special request gets saved and also visible on the layout after saved, but if we go Back to My Trips and come back to the same trip - the updated special request does not show up, this is perhaps because the API is not called and is cached by React Query. But if we refresh the page, the special request shows up.
BUG-006 | 2026-07-05 | Responsiveness | Desktop/wide ¦ Frontend | P1 | Closed | Swaroop | P1: Logout happens successfully, also cache is cleared,navigates to Login and never goes back to authenticated pages unless logged in back. A small issue is when I click on the Logout button and it slides down to the Confirmation message and the final logout message - that scroll does not fully scroll to that confirmation div and I have to again scroll to see that region and finally click on logout. This happens only in lg+ devices and not in mobiles or tablets or even smaller devices
BUG-007 | 2026-07-05 | Reserve ride | All trip types ¦ Backend | P0 | Closed | Swaroop | When a customer joins the app and does not add their email, and continues to book a trip by following the Search->Fill in preferences(date, passenger etc.)->Select options->Reserve. At the Reserve point - the front end invokes an initiate-booking endpoint which fails at the backend with an error "sraise CabboException( core.exceptions.CabboException: Failed to initiate trip booking: 1 validation error for PaymentNotesSchema customer.email value is not a valid email address: An email address must have an @-sign. [type=value_error, input_value='', input_type=str] (status_code=500)" which clearly is an email validation error during creating the payment order. Hence the screen shows a Error Boundary generic screen, but funny part is when we retry on the generic error page or refresh the page - the error does not happen any more and initiates the booking successfully.
BUG-008 | 16th August 2026 | Status matrix | All trip types | P0 | Closed | Swaroop | On opening a completed trip of any type and providing a review updates the DB and also UI reflects the changes locally from state data - but go back and again come here - it still shows - Provide review and not the recently provided review. Only after a page refresh the issue gets resolved - perhaps a react query state update issue.