## Dashboard
Cabbo Customer Frontend QA Checklist (Dev Smoke Env)
Target app | https://app.dev.cabbo.co.in
Target API | https://api.dev.cabbo.co.in
Scope | Lean smoke after extensive local QA; focus on live dev wiring and P0/P1 confidence.
Generated on | 2026-08-16 20:05
Metric | Value | Notes
Total checklist items | 29 | All smoke rows in Checklist
Passed | 29
Failed | 0 | Any P0 fail blocks prod promotion
Blocked | 0
Not started | 170
Open P0 defects | 0
Smoke Rule | Do not repeat exhaustive local QA unless a dev-only defect appears. Validate the live domains, cookies, payment callbacks, route guards, and critical booking paths.

## Test Accounts
Persona | Phone Verified | Email Verified | Use For | Login Identifier | Password / OTP Notes | Notes
Verified customer | Yes | Yes | Primary dev smoke: login, search, reserve, payment, booking detail |  | Use known dev OTP/session flow | Fill before test run
Email-unverified customer | Yes | No | Only if validating profile/email recovery in dev |  | Use known dev OTP/session flow | Optional for smoke
Admin/Ops tester | NA | NA | Confirm customer booking appears in Admin/Ops dev surface |  |  | Use admin dev URL/account if available

## Checklist
Priority | Section | Area | Trip Type | Persona | Smoke Test | Expected Result | Status | Tester | Date | Evidence Link | Issue Link | Notes
P0 | Environment | App boot | All | Either | Open https://app.dev.cabbo.co.in on a fresh browser session | App loads without white screen, fatal console errors, or asset/CORS failures | Pass | Swaroop C | 2026-08-16
P0 | Environment | API integration | All | Either | Perform one app action that calls https://api.dev.cabbo.co.in | Request succeeds over HTTPS and no mixed-content/CORS/session-cookie issue appears | Pass | Swaroop C | 2026-08-16
P0 | Routing | Public route | All | Logged-out customer | Open login/public route and refresh | Public route stays usable and does not get stuck on splash | Pass | Swaroop C | 2026-08-16
P0 | Routing | Protected route | All | Logged-out customer | Open a protected booking/detail URL while logged out | User is routed to login gracefully; no endless splash/loading loop | Pass | Swaroop C | 2026-08-16
P0 | Auth | Login | All | Verified customer | Login with a known dev customer account | OTP/session flow succeeds and customer lands in authenticated app | Pass | Swaroop C | 2026-08-16
P0 | Auth | Authenticated redirect | All | Logged-in customer | Open login route while already logged in | PublicRoute detects session and redirects to home as expected | Pass | Swaroop C | 2026-08-16
P0 | Auth | Manual logout | All | Logged-in customer | Logout from profile and refresh | Session/cache are cleared; back/refresh cannot access protected pages | Pass | Swaroop C | 2026-08-16
P1 | Auth | Expired session handling | All | Logged-in customer | Optional: invalidate dev session/cookie or wait for expiry, then trigger protected API action | 401/403 protected API response triggers centralized logout and routes to login without splash loop | Pass | Swaroop C | 2026-08-16
P0 | Geography | Fallback safety | All | Either | Load app and complete a search with dev geography services available | Server/client geography does not crash app; defaults/fallbacks remain graceful if client geo is unavailable | Pass | Swaroop C | 2026-08-16
P0 | Date/time | Trip timezone clarity | All | Logged-in customer | Search/select trip times and review booking detail refund and cancellation policy text | Displayed date/time and cancellation cutoff are understandable and in the trip timezone | Pass | Swaroop C | 2026-08-16
P0 | Search | Airport transfer options | Airport transfer | Logged-in customer | Search airport pickup/drop and click Find Ride | Loader/skeleton appears during handoff and ride options render correctly | Pass | Swaroop C | 2026-08-16
P0 | Search | Local hourly options | Local hourly rental | Logged-in customer | Search local hourly rental and click Find Ride | Loader/skeleton appears during handoff and ride options render correctly | Pass | Swaroop C | 2026-08-16
P0 | Search | Outstation options | Outstation | Logged-in customer | Search outstation route/dates and click Find Ride | Loader/skeleton appears during handoff and ride options render correctly | Pass | Swaroop C | 2026-08-16
P0 | Booking | Reserve ride | Airport transfer | Logged-in customer | Select an airport option and reserve ride | Booking initiation succeeds and payment/order handoff starts | Pass | Swaroop C | 2026-08-16
P0 | Booking | Reserve ride | Local hourly rental | Logged-in customer | Select a local hourly option and reserve ride | Booking initiation succeeds and payment/order handoff starts | Pass | Swaroop C | 2026-08-16
P0 | Booking | Reserve ride | Outstation | Logged-in customer | Select an outstation option and reserve ride | Booking initiation succeeds and payment/order handoff starts | Pass | Swaroop C | 2026-08-16
P0 | Payment | Success path | Any one trip type | Logged-in customer | Complete a dev/test payment successfully | Return/callback creates confirmed booking and app shows correct booking detail | Pass | Swaroop C | 2026-08-16
P0 | Payment | Failure/cancel path | Any one trip type | Logged-in customer | Cancel/fail payment from checkout if supported in dev | Customer sees recoverable state; no duplicate confirmed booking is created | Pass | Swaroop C | 2026-08-16
P0 | My Trips | Feed and navigation | All | Logged-in customer | Open My Trips after booking and navigate to detail | Booking appears in correct order/status and detail page opens from feed | Pass | Swaroop C | 2026-08-16
P0 | Booking detail | Core details | All | Logged-in customer | Open a confirmed booking detail | Pickup/drop, passenger/trip preferences, fare, payment status, and policy sections are correct | Pass | Swaroop C | 2026-08-16
P1 | Booking detail | Inclusions/exclusions | All | Logged-in customer | Review structured inclusions/exclusions on a newly created booking | Labels, descriptions, and icons render; legacy string fallback is not broken | Pass | Swaroop C | 2026-08-16
P1 | Booking detail | Driver card | Assigned-driver booking | Logged-in customer | Open booking with assigned driver across upcoming/ongoing states if available | Contact actions, coordination hint, live ongoing label, and safe driver details behave by status | Pass | Swaroop C | 2026-08-16
P1 | Booking detail | Upgrade messaging | Assigned-driver booking | Logged-in customer | Open booking where assigned cab/fuel differs from preference if available | Server upgrade message appears; fallback message is graceful only when eligible | Pass | Swaroop C | 2026-08-16
P1 | Booking detail | Special request persistence | Eligible booking | Logged-in customer | Add/update a special request, leave detail, and reopen it | Updated request persists without requiring a full page refresh | Pass | Swaroop C | 2026-08-16
P1 | Booking detail | Review cache update | Completed trip | Logged-in customer | Submit a trip review, go back, and reopen detail | Provided review remains visible without requiring page refresh | Pass | Swaroop C | 2026-08-16
P0 | Error handling | Not found/invalid booking | All | Logged-in customer | Open an invalid booking detail URL | Trip-not-found or graceful error state appears; ErrorBoundary does not unnecessarily kill the app | Pass | Swaroop C | 2026-08-16
P1 | Responsiveness | Mobile smoke | All | Logged-in customer | Run login, search, option selection, and booking detail on a mobile viewport/device | Primary actions are visible, no overlap, skeleton/detail sections remain polished | Pass | Swaroop C | 2026-08-16
P1 | Responsiveness | Desktop smoke | All | Logged-in customer | Run search/options/detail/profile logout on desktop viewport | Layouts remain aligned and logout/profile flows are usable | Pass | Swaroop C | 2026-08-16
P1 | Ops readiness | Admin/Ops handoff visibility | Any booked trip | Internal/dev tester | Confirm created dev booking is visible/operable in Admin/Ops dev surface | Admin/Ops can see booking details, payment state, customer notes, and status controls for fulfilment | Pass | Swaroop C | 2026-08-16

## Defects Log
ID | Date | Checklist Row / Area | Segment | Severity | Status | Owner | Notes